## Pre-Meeting
Meeting Department Services Checklist and Planning Timeline- Virtual meetings
Tasks | Timeline | Responsible staff | Date completed | Notes
Meetings Department
Meeting request form received | at least six months | Project Manager
Meeting added to the meeting calendar | 24 hours of receipt | Meetings
Meeting planner assigned | 48 hours of receipt | Meetings
Cross team kick off meeting | 2 weeks after receipt of MRF | Meetings
Budget Review | during kick-off meeting | Project Manager/Meetings
Program & Content
Collect speaker bios and photos, overview page | after MRF is submitted | Project Manager
Submit overview page and session information through Workfront | 4 months prior to the meeting | Project Manager
Content edited by Marketing team | 1-2 weeks after submitted through Workfront | Brand Engagement
Fonteva event page created by Meetings team (overview, agenda, registration) | 1 week after receiving edited information | Meetings
Fonteva registration testing | after retgistration is set-up | Project Manager/Meetings
Content editor creates landing page for aia.org events tab | after the Fonteva registration page testing is complete | Content Governance
Review of aia.org event post | allow two-day turnaround after the event is submitted to CG for review | Content Governance
Registration is open email and other reminder emails | 3 months before the meeting | Brand Engagement

## Registration
Meeting Department Services Checklist and Planning Timeline- Virtual meetings
Registration | Timeline | Deadline Date | Date Completed
Online general information template | 24 hours after content is edited by Marketing
Registration opens | 3 months before meeting starts
Registration reports | Weekly after registration is open
Pre-conference email
Special Needs (ADA)

## Post Meeting
Meeting Department Services Checklist and Planning Timeline- Virtual meetings
Post-Meeting | Timeline | Deadline Date | Date Completed
Review hotel/all bills; prepare invoices | Within 30 days
Final Reports | Within 30 days
Final registration reports | 3 weeks after event ends
Update calendars with numbers | 3 weeks after event ends
CES reports (if applicable)
Thank you letters | 2 weeks
Wrap-up meeting with Project Manager | 1 week
Attendee survey | 1 week
Zoomerang survey for Project Manager | 1 week